## Project description
Short description | Technologies stack
Interactive Movie Databases aka IMDB | Angular
Spring Boot
Spring security
Spring boot data
Postgres

## Schedule
Project: interactive Movie Databases aka IMDB
Week/Scope | 18-May | 25-May | 1-Jun | 8-Jun | 15-Jun | 22-Jun | 29-Jun | 6-Jul | 13-Jul
DB design. Concept discussion
Prototyping. First request/response. E.g. "Get All Users"
Cover all necessary scenarious
Client part - Angular
Unit tests, code analysis, bugfix
Enhancements
Connection with 3rd party DB, reconcillation
BugFix, stabilization